Topic 3: Budgeting Activity

You have been awarded a grant to undertake a scientific research project to be conducted in conjunction with an eco-tourism initiative as part of the Murray-Darling research project. In your grant application, you sought $300,000. The project is to be completed this academic year.

Your budgeted expenditure for the project is as follows:

| Staff Member | Yearly Salary | Additional Information |
| --- | --- | --- |
| Chief Investigator – Dr Allison | $110,895 | Days required 125 On cost rate – 34.27% |
| Dr Black | $107,614 | Days required 70 On cost rate – 25.70% |
| Dr Stuart | $107,614 | Days required 70 On cost rate – 25.60% |
| Mr. Van Driver | $57,947 | Days required 50 On cost rate – 15.59% |

You have allowed $10,000 for attendance at a conference in San Francisco to be held in October 2008.

Equipment:

You are budgeting for the following costs:					$

New equipment							          10,000

Equipment usage								5,000

Lab – glassware								1,000

Lab – gases									1,000

Lab – gas cylinder hire							   500

Lab- other consumables							2,000

Safety equipment								1,000

Waste disposal								2,000

Freight and packaging							5,000

Facilities:

Recovery – lab usage							20,000

Recovery – special facilities –wind tunnel					 5,000

Recovery – IT –specialised software					25,000

Using the spreadsheet provided, prepare a budget for the project.

How would you manage this budget as the research project proceeds, and what do you need to discuss with your Dean?